## Task Checklist
CULTURE FOUNDRY ¦ OPTIMIZATION TASK CHECKLIST & SCHEDULE ¦ What Works Marketing ¦ August 2026
Section | Order | Task / Deliverable | Work Type | Priority | Status (from review) | Notes | Depends On | Assigned To | Done?
A) Google Business Profiles
A) Google Business Profiles | a | Define a simple, repeatable review-request process (who asks, when, wording, link) | Strategy | 1 | URGENT | Seattle has 1 review; Austin has 0. Reviews are among the strongest local ranking and conversion factors.
A) Google Business Profiles | b | Request and collect Google reviews from recent and long-standing clients (both profiles) | Implementation | 1 | URGENT | Client-side effort with our prompts. Aim for steady drip, not a one-time burst. | A-a
A) Google Business Profiles | c | Add quality photos to Seattle and Austin profiles (team, workspace, exterior) | Implementation | 1 | URGENT | Seattle: 1 photo + street view. Austin: street view only.
A) Google Business Profiles | d | Add core services to both profiles (web design, web development, managed hosting, etc.) | Implementation | 1 | URGENT | No services listed on either profile. Gives Google more to match against. | B-a
A) Google Business Profiles | e | Draft 750-character business descriptions for each profile, including main services | Content | 2 | OK but could use improvement | Align wording with the citation template so descriptions match across the web. | B-a
A) Google Business Profiles | f | Publish descriptions to both profiles | Implementation | 2 | OK but could use improvement |  | A-e
A) Google Business Profiles | g | Align hours: confirm 24-hour weekday listing, then display matching hours on the website | Implementation | 2 | OK but could use improvement | GBP shows open 24 hours Mon-Fri; site shows no hours. If 24h reflects support coverage, say so plainly on the site.
A) Google Business Profiles | h | Review secondary categories (currently web hosting company, software company, internet marketing service) | Strategy | 3 | OK but could use improvement | Confirm the mix matches the searches we most want to win.
A) Google Business Profiles | i | Define service-area approach for Portland, Boulder, and Sarasota (no physical offices) | Strategy | 3 | New (from review) | Lighter touch: service-area settings on existing profiles plus pages framed around serving those markets. No new profiles needed.
B) Off-Site Signals
B) Off-Site Signals | a | Standardize the official NAP: one business name (Culture Foundry vs Culture Foundry LLC), one address format, one phone format | Strategy | 1 | Checked - needs attention | Must be locked before citation work. Feeds GBP, citations, footer, and schema. This is entity resolution for the Knowledge Graph.
B) Off-Site Signals | b | Citation cleanup: correct the old Seattle address (5101 14th Ave NW) to 600 N 36th St #200 across directories | Implementation | 1 | URGENT | Old address dominates directories; several Austin listings even carry Seattle addresses. Inconsistent citations can be worse than missing ones. | B-a
B) Off-Site Signals | c | Citation submissions for Seattle (target 40+ score; currently 26/100) | Implementation | 2 | URGENT | Well-understood, repeatable work. Combine with cleanup in one project. | B-a
B) Off-Site Signals | d | Citation submissions for Austin (target 40+ score; currently 23/100) | Implementation | 2 | URGENT |  | B-a
B) Off-Site Signals | e | Re-check citation scores after project completes; confirm both locations at 40+ | Implementation | 3 | Follow-up | Schedule for ~6-8 weeks after submissions. | B-c, B-d
B) Off-Site Signals | f | Backlink and keyword gap analysis vs competing agencies | Strategy | 3 | Recommendation | Points the on-site and content work at the highest-value targets. Recommendation rather than a finding.
C) Technical Health
C) Technical Health | a | Compress oversized images (27 images at 1MB+) | Web Development | 2 | Checked - needs attention | Clearest technical quick win. No visual change; lifts lab scores and protects speed as the site grows. File list available.
C) Technical Health | b | Draft revised page titles and H1s (titles over 60 chars incl. critical pages; duplicates on blog/crew pages; short titles on resource pages; 2 service pages missing H1s) | Content | 2 | Checked - needs attention | Pairs with the on-site title work. Detail files available for each issue.
C) Technical Health | c | Apply revised titles and H1s in the CMS | Implementation | 2 | Checked - needs attention |  | C-b
C) Technical Health | d | Resolve multiple H1s on resource pages (template-level fix) | Web Development | 3 | OK but could use improvement
C) Technical Health | e | Build out thin content pages (includes at least one service page) | Content | 3 | Checked - needs attention | Fold into the cluster/content work in Section E where possible. | E-a
C) Technical Health | f | Fix internal links pointing to 404 pages | Web Development | 3 | OK but could use improvement | Small count. File available.
C) Technical Health | g | Verify the canonicalized blog post is intentional | Web Development | 3 | OK but could use improvement | One page involved.
C) Technical Health | h | Live review of interaction responsiveness (INP) | Web Development | 3 | Merits live review | Testing-tool reading came in above Google's threshold, but tool ratings often run much slower than real-life conditions. Confirm live before acting.
D) On-Site Optimization & Structure
D) On-Site Optimization & Structure | a | Update sitewide footer: replace old Seattle address with current one; consider showing both offices | Web Development | 1 | Checked - needs attention | Our own site currently contradicts Google's address for Seattle. Must match GBP character-for-character. | B-a
D) On-Site Optimization & Structure | b | Link the home page service summaries to their service pages | Web Development | 2 | Checked - needs attention | Small change, real impact. Passes authority to the pages that generate inquiries.
D) On-Site Optimization & Structure | c | Draft a plain-language, extractable statement of what Culture Foundry is, does, and serves (home page, high on page) | Content | 2 | OK but could use improvement | Sits alongside 'reclaim the power of tech', not replacing it. Serves crawlers, AI tools, and first-time visitors.
D) On-Site Optimization & Structure | d | Insert the plain-language statement into the home page template | Web Development | 2 | OK but could use improvement |  | D-c
D) On-Site Optimization & Structure | e | Decide which services are the priority for visibility (informs nav, home page, linking) | Strategy | 2 | OK but could use improvement | Current structure treats all services evenly; machines can't tell what matters most. | B-f
D) On-Site Optimization & Structure | f | Adjust navigation and internal linking to elevate priority services | Web Development | 3 | OK but could use improvement |  | D-e
D) On-Site Optimization & Structure | g | Add full street addresses to Seattle and Austin location pages (matched to GBP) | Implementation | 2 | OK but could use improvement | Portland, Boulder, Sarasota pages stay lighter, framed as service-area pages. | B-a
D) On-Site Optimization & Structure | h | Reframe Portland, Boulder, and Sarasota pages as service-area pages | Content | 3 | New (from review) | Light optimization language: serving the market, time zone coverage. No fabricated office signals. | A-i
D) On-Site Optimization & Structure | i | Contact page: embed each office's Google Business Profile | Web Development | 3 | Checked - needs attention | Closes the loop between site and profile.
D) On-Site Optimization & Structure | j | Contact page: make phone number clickable; show full name and address (NAP) | Web Development | 3 | Checked - needs attention | Footer phone is clickable; contact page phone is not. NAP not visible on contact page. | B-a
E) Content & Blog Strategy (Cultivate)
E) Content & Blog Strategy (Cultivate) | a | Topic cluster strategy: map existing Cultivate posts against target commercial topics; define clusters, pillars, and gaps | Strategy | 2 | New (from review) | Anchored by the tracked keyword list (enterprise web dev, WordPress/Drupal, performance, UX). The engine for closing the visibility gap. | B-f
E) Content & Blog Strategy (Cultivate) | b | Category structure research: identify the best category structure to support the clusters | Strategy | 2 | Checked Good (structure exists); optimize | Categories and custom category pages exist. Confirm they map cleanly to target topics before deeper work. | E-a
E) Content & Blog Strategy (Cultivate) | c | Enable static intro content and headings on category page templates | Web Development | 2 | New (from review) | Development work so each category page can carry a proper introduction, curated posts, and service links. | E-b
E) Content & Blog Strategy (Cultivate) | d | Draft optimized intro content for each category page (plain topic naming, links to matching services) | Content | 2 | New (from review) | Turns each category page into a genuine mid-level hub landing page. | E-b, E-c
E) Content & Blog Strategy (Cultivate) | e | Publish category content and recategorize posts as needed | Implementation | 2 | New (from review) |  | E-d
E) Content & Blog Strategy (Cultivate) | f | Author authority plan: choose regular authors; gather credentials, experience, domain focus, photos, external profiles | Strategy | 2 | Checked - needs attention | Bylines, archive pages, and Person schema exist. Real bios do not. Biggest E-E-A-T gap on the site.
E) Content & Blog Strategy (Cultivate) | g | Build author bio page template (photo, credentials, focus, external profile links) | Web Development | 2 | Checked - needs attention |  | E-f
E) Content & Blog Strategy (Cultivate) | h | Draft author bios with specific, verifiable detail and LinkedIn/publication links | Content | 2 | Checked - needs attention | Specificity is the differentiator. External links let machines verify the person is real. | E-f
E) Content & Blog Strategy (Cultivate) | i | Publish bios and connect every byline to its bio page | Implementation | 2 | Checked - needs attention |  | E-g, E-h
E) Content & Blog Strategy (Cultivate) | j | Add internal links from Cultivate posts to matching service pages | Implementation | 2 | Checked - needs attention | Posts currently link out but not to service pages. Which links go where comes from the cluster map. | E-a
E) Content & Blog Strategy (Cultivate) | k | Edit key posts to lead with a short, direct answer | Content | 3 | OK but could use improvement | AI tools extract from the top of a page. Prioritize the strongest cluster posts. | E-a
E) Content & Blog Strategy (Cultivate) | l | Produce new cluster posts to fill topic gaps (ongoing) | Content | 3 | New (from review) | Ongoing cadence once clusters are defined. | E-a
F) Schema Markup
F) Schema Markup | a | LocalBusiness schema on home page and Seattle/Austin location pages (NAP character-for-character with GBP, hours, geo, areaServed) | Web Development | 2 | Checked - needs attention | The big one for a multi-office firm. Covers the 'NAP in schema' item. Must follow the address standardization. | B-a, D-a
F) Schema Markup | b | Service schema on each service page | Web Development | 2 | Checked - needs attention | States plainly what the firm offers; pairs with on-site and cluster work.
F) Schema Markup | c | Enhance Person schema: link authors to bio pages; add sameAs links to external profiles | Web Development | 3 | Checked - needs attention | Turns visible bylines into explicit machine signals. | E-i
F) Schema Markup | d | BreadcrumbList schema on all pages except home | Web Development | 3 | Checked - needs attention | Reinforces hierarchy; improves listing display.
F) Schema Markup | e | Consolidate on JSON-LD: remove older microdata emitted by the navigation | Web Development | 3 | OK but could use improvement | Tidy-up rather than a fault. Existing JSON-LD validates cleanly.
F) Schema Markup | f | FAQPage schema wherever FAQs are published | Web Development | 3 | Checked - needs attention | Only mark up Q&As that appear visibly on the page. | G-e
G) Answer Engine Optimization
G) Answer Engine Optimization | a | Add answer-first intros to key service pages (short, plain summary of what the page covers and who it's for) | Content | 2 | OK but could use improvement | Home page covered in D-c/D-d. This row covers service and solution pages. | D-e
G) Answer Engine Optimization | b | State the track record in plain numbers on company and home pages (years in business, client/project volume) | Content | 2 | Checked - needs attention | Specifics outperform 'established agency' for both readers and machines. Not currently stated anywhere.
G) Answer Engine Optimization | c | FAQ strategy: choose which service pages get short FAQs, page by page | Strategy | 3 | Checked - needs attention | Note: marketer overuse has led Google to reduce FAQ prominence. Still valuable in moderation where they genuinely help the visitor. Short FAQs on service pages, not a standalone FAQ page.
G) Answer Engine Optimization | d | Draft FAQs for chosen pages (bold question, clear direct answer) | Content | 3 | Checked - needs attention | That format is the most reliably extractable structure for AI tools. | G-c
G) Answer Engine Optimization | e | Publish FAQs on the chosen pages | Implementation | 3 | Checked - needs attention | Schema added in F-f. | G-d
G) Answer Engine Optimization | f | Original data concept: identify a study or dataset only Culture Foundry can publish (performance work, migrations, hosting data) | Strategy | 3 | Checked - needs attention | Original data is the strongest citation signal. Makes CF a primary source. Even one strong piece per year matters.
G) Answer Engine Optimization | g | Produce and publish the original research piece | Content | 3 | Checked - needs attention |  | G-f
G) Answer Engine Optimization | h | Keep llms.txt current as site structure and priority pages change | Implementation | 4 | Checked Good (maintain) | Already published, which is ahead of the curve. Light ongoing maintenance.
LEGEND
Priority (impact:effort)
1 | 1 - Emergency: do right away
2 | 2 - Important: absolutely should be addressed
3 | 3 - Less critical: do when possible
4 | 4 - If and when time allows
Work Type
Strategy | Research, decisions, and planning
Web Development | Code, theme, and template changes
Content | Drafting optimized copy, bios, posts, FAQs
Implementation | Hands-on setup: GBP edits, citations, plugin config, publishing
How to use: fill in 'Assigned To' with a name and mark 'Done?' with Yes when complete. Example: Assigned To = 'Rob', Done? = 'Yes'. 'Depends On' references Section-Order codes (e.g. B-a = Off-Site task a). Sort or filter by Priority or Work Type using the header dropdowns.