## README
Fortra Automate — Phase 2: Items needing your input
Background:
When we did the original audit on 2026-04-23 you sent us back decisions on 27 broken /node/N links.
We started implementing all 400+ link/redirect fixes on 2026-05-05. Before doing the bulk run we
re-verified every source URL and target URL against the live site, since 12 days had passed.
What we found: about 14% of the planned edits had drifted — either the source URL no longer
redirects (someone published a node at that path), or the proposed target now returns 403/404.
These edits need fresh decisions before we can apply them safely.
What we already did:
• All 12 redirect chain flattens (T015) — done & verified
• 4 sample link updates done & verified (Edit #1-#4)
• Master worklist built showing every planned edit + status (master_worklist.csv)
What this workbook contains:
Tab 2 — "Academy URLs (50)": Both source AND proposed target now return 403. The /product-lines/automate/academy/
tree appears to have been migrated/restricted. We need your call: remove these links entirely, or
tell us where they should point now.
Tab 3 — "Drifted T063 (8)": Legacy /node/N targets whose canonical alias now returns 404/403.
Tab 4 — "T016 Caution (8)": Source still redirects but to a different first hop than we originally recorded.
Mostly URL-truncation artifacts in our original CSV (the %e2%80%a6 ellipsis in URLs).
Note about Edit #2 (the demo CTA we already updated):
We changed REQUEST A DEMO from /products/automate-desktop/demo to /demo. At audit time, the source URL
was a 301 redirect to /demo. NOW, /products/automate-desktop/demo serves a real (but unpublished/restricted)
page, so anonymous users get 403. The fix is still correct — /demo is the canonical demo page — but worth
flagging so you know the audit landscape has shifted on the live site.

## Academy URLs (50)
These are links pointing into the /product-lines/automate/academy/ tree. Both the link source AND | the URL we proposed to fix it to now return 403. The academy content seems to have been moved or paywalled. | Please decide for each: REMOVE the link entirely, or provide a new URL.
Page (NID) | Page URL | Link text | Current href (broken) | Originally proposed (also broken) | YOUR DECISION (REMOVE or new URL)
13505 | /resources/articles/getting-started-automate-free-trial | Overview of Tasks | /product-lines/automate/academy/automate101/chapter3 | https://www.fortra.com/product-lines/automate/academy/developer/basic-concepts
19285 | /blog/pros-and-cons-python-web-automation | website automation | /product-lines/automate/academy/automateessentials/chapter5 | https://www.fortra.com/product-lines/automate/academy/developer/ui-automation
28240 | /blog/desktop-automation-4-small-tasks-automate-big-impact | website automation | https://automate.fortra.com/product-lines/automate/academy/automateessentials/chapter5 | https://www.fortra.com/product-lines/automate/academy/developer/ui-automation
17281 | /resources/datasheets/automate-desktop-overview | WEB BROWSER TASK AUTOMATION | /product-lines/automate/academy/automateessentials/chapter5 | https://www.fortra.com/product-lines/automate/academy/developer/ui-automation
17432 | /resources/academy/triggers | Chapter 1: Overview of Triggers | /product-lines/automate/academy/triggers/chapter1 | https://www.fortra.com/product-lines/automate/academy/developer/basic-concepts
17432 | /resources/academy/triggers | Chapter 2: Schedule Trigger H | /product-lines/automate/academy/triggers/chapter2 | https://www.fortra.com/product-lines/automate/academy/developer/triggers
17432 | /resources/academy/triggers | Chapter 3: File Trigger How t | /product-lines/automate/academy/triggers/chapter3 | https://www.fortra.com/product-lines/automate/academy/developer/triggers
17432 | /resources/academy/triggers | Chapter 4: Email Trigger How | /product-lines/automate/academy/triggers/chapter4 | https://www.fortra.com/product-lines/automate/academy/developer/triggers
17432 | /resources/academy/triggers | Chapter 5: Database Trigger H | /product-lines/automate/academy/triggers/chapter5 | https://www.fortra.com/product-lines/automate/academy/developer/triggers
17432 | /resources/academy/triggers | Chapter 6: Startup Trigger Ho | /product-lines/automate/academy/triggers/chapter6 | https://www.fortra.com/product-lines/automate/academy/developer/triggers
17432 | /resources/academy/triggers | Chapter 7: Window Trigger How | /product-lines/automate/academy/triggers/chapter7 | https://www.fortra.com/product-lines/automate/academy/developer/triggers
17432 | /resources/academy/triggers | Chapter 8: Keyboard Trigger H | /product-lines/automate/academy/triggers/chapter8 | https://www.fortra.com/product-lines/automate/academy/developer/triggers
17432 | /resources/academy/triggers | Chapter 9: Event Log Trigger | /product-lines/automate/academy/triggers/chapter9 | https://www.fortra.com/product-lines/automate/academy/developer/triggers
17432 | /resources/academy/triggers | Chapter 10: Process Trigger H | /product-lines/automate/academy/triggers/chapter10 | https://www.fortra.com/product-lines/automate/academy/developer/triggers
17432 | /resources/academy/triggers | Chapter 11: Service Trigger H | /product-lines/automate/academy/triggers/chapter11 | https://www.fortra.com/product-lines/automate/academy/developer/triggers
17620 | /resources/academy/tasks | Chapter 2: Database to Excel | /product-lines/automate/academy/tasks/chapter2 | https://www.fortra.com/product-lines/automate/academy/developer/native-actions
17620 | /resources/academy/tasks | Chapter 3: Interactivity Report | /product-lines/automate/academy/tasks/chapter3 | https://www.fortra.com/product-lines/automate/academy/developer/ui-automation
17620 | /resources/academy/tasks | Chapter 4: Excel to SQL How t | /product-lines/automate/academy/tasks/chapter4 | https://www.fortra.com/product-lines/automate/academy/developer/native-actions
17620 | /resources/academy/tasks | Chapter 5: File Transfer Automation | /product-lines/automate/academy/tasks/chapter5 | https://www.fortra.com/product-lines/automate/academy/developer/native-actions
17620 | /resources/academy/tasks | Chapter 6: Web Browser Automation: Login | /product-lines/automate/academy/tasks/chapter6 | https://www.fortra.com/product-lines/automate/academy/developer/ui-automation
17620 | /resources/academy/tasks | Chapter 7: Web Browser Automation: Extract Data | /product-lines/automate/academy/tasks/chapter7 | https://www.fortra.com/product-lines/automate/academy/developer/ui-automation
17620 | /resources/academy/tasks | Chapter 8: Web Browser Automation: Best Practices | /product-lines/automate/academy/tasks/chapter8 | https://www.fortra.com/product-lines/automate/academy/developer/ui-automation
17620 | /resources/academy/tasks | Chapter 9: PDF to Excel How t | /product-lines/automate/academy/tasks/chapter9 | https://www.fortra.com/product-lines/automate/academy/developer/native-actions
17620 | /resources/academy/tasks | Chapter 10: Email Capture How | /product-lines/automate/academy/tasks/chapter10 | https://www.fortra.com/product-lines/automate/academy/developer/native-actions
17620 | /resources/academy/tasks | Chapter 11: CSV to Excel How | /product-lines/automate/academy/tasks/chapter11 | https://www.fortra.com/product-lines/automate/academy/developer/native-actions
20563 | /resources/automate/academy/automateessentials | Chapter 1: File System Automation | /product-lines/automate/academy/automateessentials/chapter1 | https://www.fortra.com/product-lines/automate/academy/developer/native-actions
20563 | /resources/automate/academy/automateessentials | Chapter 2: Dataset Action In | /product-lines/automate/academy/automateessentials/chapter2 | https://www.fortra.com/product-lines/automate/academy/developer/basic-concepts
20563 | /resources/automate/academy/automateessentials | Chapter 4: Spreadsheet Automation | /product-lines/automate/academy/automateessentials/chapter4 | https://www.fortra.com/product-lines/automate/academy/developer/native-actions
20563 | /resources/automate/academy/automateessentials | Chapter 5: Web Browser Automation | /product-lines/automate/academy/automateessentials/chapter5 | https://www.fortra.com/product-lines/automate/academy/developer/ui-automation
20563 | /resources/automate/academy/automateessentials | Chapter 6: Terminal Emulation | /product-lines/automate/academy/automateessentials/chapter6 | https://www.fortra.com/product-lines/automate/academy/developer/native-actions
20563 | /resources/automate/academy/automateessentials | Chapter 7: Looping & Conditional Logic | /product-lines/automate/academy/automateessentials/chapter7 | https://www.fortra.com/product-lines/automate/academy/developer/advanced-concep…
20563 | /resources/automate/academy/automateessentials | Chapter 8: Database Automation | /product-lines/automate/academy/automateessentials/chapter8 | https://www.fortra.com/product-lines/automate/academy/developer/native-actions
15704 | /resources/academy/automate101 | Chapter 1: Getting Started with Automate | /product-lines/automate/academy/automate101/chapter1 | https://www.fortra.com/product-lines/automate/academy/developer/basic-concepts
15704 | /resources/academy/automate101 | Chapter 3: Overview of Tasks | /product-lines/automate/academy/automate101/chapter3 | https://www.fortra.com/product-lines/automate/academy/developer/basic-concepts
15704 | /resources/academy/automate101 | Chapter 4: Overview of Workflows | /product-lines/automate/academy/automate101/chapter4 | https://www.fortra.com/product-lines/automate/academy/developer/basic-concepts
15704 | /resources/academy/automate101 | Chapter 5: Overview of Actions | /product-lines/automate/academy/automate101/chapter5 | https://www.fortra.com/product-lines/automate/academy/developer/basic-concepts
15704 | /resources/academy/automate101 | Chapter 6: Overview of Triggers | /product-lines/automate/academy/automate101/chapter6 | https://www.fortra.com/product-lines/automate/academy/developer/basic-concepts
15704 | /resources/academy/automate101 | Chapter 7: Getting Started with System Settings | /product-lines/automate/academy/automate101/chapter7 | https://www.fortra.com/product-lines/automate/academy/developer/basic-concepts
15704 | /resources/academy/automate101 | Chapter 8: Getting Started with Server Settings for Automate Enterprise | /product-lines/automate/academy/automate101/chapter8 | https://www.fortra.com/product-lines/automate/academy/developer/basic-concepts
15704 | /resources/academy/automate101 | Chapter 9: Variables, Datasets, and the Expression Builder | /product-lines/automate/academy/automate101/chapter9 | https://www.fortra.com/product-lines/automate/academy/developer/basic-concepts
15704 | /resources/academy/automate101 | Chapter 10: How to Use the Automate Recorder for Desktop Interactivity | /product-lines/automate/academy/automate101/chapter10 | https://www.fortra.com/product-lines/automate/academy/developer/basic-concepts
15704 | /resources/academy/automate101 | Chapter 11: How to Use the Automate Recorder for Web Browser Interactivity | /product-lines/automate/academy/automate101/chapter11 | https://www.fortra.com/product-lines/automate/academy/developer/basic-concepts
18046 | /resources/academy/advancedconcepts | Chapter 1: Error Handling How | /product-lines/automate/academy/advancedconcepts/chapter1 | https://www.fortra.com/product-lines/automate/academy/developer/advanced-concep…
18046 | /resources/academy/advancedconcepts | Chapter 2: Inheritance How to | /product-lines/automate/academy/advancedconcepts/chapter2 | https://www.fortra.com/product-lines/automate/academy/developer/advanced-concep…
18046 | /resources/academy/advancedconcepts | Chapter 3: Deploying and Automating Agents | /product-lines/automate/academy/advancedconcepts/chapter3 | https://www.fortra.com/product-lines/automate/academy/administrator/basic-conce…
18046 | /resources/academy/advancedconcepts | Chapter 4: Functions and Subtasks | /product-lines/automate/academy/advancedconcepts/chapter4 | https://www.fortra.com/product-lines/automate/academy/developer/advanced-concep…
17435 | /product-lines/automate/academy/triggers/chapter3 | WATCH NOW | /product-lines/automate/academy/triggers/chapter4 | https://www.fortra.com/product-lines/automate/academy/developer/triggers
17433 | /product-lines/automate/academy/triggers/chapter2 | WATCH NOW | /product-lines/automate/academy/triggers/chapter3 | https://www.fortra.com/product-lines/automate/academy/developer/triggers
17434 | /product-lines/automate/academy/triggers/chapter1 | WATCH NOW | /product-lines/automate/academy/triggers/chapter2 | https://www.fortra.com/product-lines/automate/academy/developer/triggers
17619 | /product-lines/automate/academy/tasks/chapter1 | WATCH NOW | /product-lines/automate/academy/tasks/chapter2 | https://www.fortra.com/product-lines/automate/academy/developer/native-actions

## Drifted T063 (8)
These are legacy /node/N links where the target node's canonical URL now 404s or 403s. | For each: REMOVE the link, or provide a new URL.
Page (NID) | Page URL | Link text | Current href | Originally proposed (now broken) | YOUR DECISION
13505 | /resources/articles/getting-started-automate-free-trial | See the complete list of sample tasks and workflows | /node/15769 | https://connectors.fortra.com/
21163 | /blog/how-make-sense-front-end-and-back-end-automation | workload automation | /node/18377 | /solutions/automation/workload-automation
24226 | /products/automate-plus/trial/thank-you | Schedule your demo today! | /node/13343 | /products/automate-plus/demo
26701 | /paragraph-types/examples-options | fortra.com/platform | /node/26506 | /platform
26701 | /paragraph-types/examples-options | fortra.com/platform | /node/26506 | /platform
26701 | /paragraph-types/examples-options | fortra.com/platform | /node/26506 | /platform
26701 | /paragraph-types/examples-options | fortra.com/platform | /node/26506 | /platform
26701 | /paragraph-types/examples-options | fortra.com/platform | /node/26506 | /platform

## T016 Caution (8)
These source URLs still redirect, but to a different target than we originally recorded. | Most are likely fine to update to the same target as the source's actual current 301 destination. | A few have URL-encoded ellipsis (%e2%80%a6) suggesting the original audit truncated long URLs.
Page (NID) | Page URL | Link text | Current href | Original proposed target | YOUR DECISION
15695 | /resources/articles/automate-bridges-gap-between-disparate-applications | LEARN MORE | /product-lines/automate | /es/lineas-de-producto/automate
15849 | /resources/articles/automating-terminal-emulation | LEARN MORE | /product-lines/automate | /es/lineas-de-producto/automate
22162 | /solutions/robotic-process-automation/hr | Automate | /product-lines/automate | /es/lineas-de-producto/automate
14223 | /industries/insurance | READ THE WHOLE STORY | /customer-stories/IT-automation-insurance-company-keeps-business-processes-running | /resources/case-studies/it-automation-insurance-company-keeps-business-processe%e2%80%a6
22409 | /solutions/robotic-process-automation/implementation/choosing-rpa-vendor | Fortra Recognized Again in Gartner 2020 Magic Quadrant for Robotic Process Autom | /about/news/helpsystems-recognized-again-gartner-2020-magic-quadrant-robotic-process-automation | /resources/press-releases/helpsystems-recognized-again-gartner-2020-magic-quadr%e2%80%a6
22409 | /solutions/robotic-process-automation/implementation/choosing-rpa-vendor | Big News! The Software Reviews 2020 Robotic Process Automation Data Quadrant is | /blog/big-news-software-reviews-2020-robotic-process-automation-data-quadrant-report | /resources/articles/big-news-software-reviews-2020-robotic-process-automation-d%e2%80%a6
20107 | /about/partner/become-a-partner/thank-you | Automate product page | /product-lines/automate | /es/lineas-de-producto/automate
20967 | /node/20967 | Automate | /product-lines/automate | /es/lineas-de-producto/automate