## Master
Program Copy | < - Program Copy Link
Master Programs - Planning Status
TEAM - Session host | Time | WHEN - Session Timing & Planning Status |  |  |  | WHO - Speaker info | WHAT - Session details |  | Notes
Host / MC / Moderator |  | Session Block | Track | Room | Status- Overall for session | Speaker | Session Title | Technical Rating
| 9:15 - 10:00am | 1 Welcome & Morning Keynote | Stage | Main Theatre | Confirmed, details in progress | Diane Gutiw | TBD |  | Diane has confirmed and is awaiting our direction on what to cover
| 10:15am - 11:00am | 2 Block A | Stage | Main Theatre | Ready to announce | Sid Shrinivasan | AI Advancements in Antibody-Based Drug Development: From Target to Clinical Candidate | 2
| 10:15am - 11:00am | 2 Block A | Builder Deeper | Oak Bay | Ready to announce | Emma Irwin | Power Back to Communities: AI Alignment for Open Source | 1
| 10:15am - 11:00am | 2 Block A | Work Smarter | Saanich | Ready to announce | Anthony Bortolussi | AI for Video Production & Editing: From Trend Mining to Final Delivery | 1 | Anthony requires travel expenses (from Vancouver) to be covered
| 10:15am - 11:00am | 2 Block A | Lead Adoption | Esquimalt | Confirmed, details in progress | Chace Cade | Keep the Same Team. 10x the Output. What Enterprise AI Actually Looks Like. | 2? | Sam spoke with Chris on Aug 21 and he said he still wanted to be involved
| 11:15am - 12:00pm | 3 Block B | Stage | Main Theatre | Ready to announce | Kris Krüg | Field Notes From the Rooms Where AI Gets Real | 1
| 11:15am - 12:00pm | 3 Block B | Builder Deeper | Oak Bay | Confirmed, details in progress | Panel Moderator: Jon Oram Speakers: Rene Fournier, etc. | Code is Cheap, Now What?
| 11:15am - 12:00pm | 3 Block B | Work Smarter | Saanich | Ready to announce | Rob Parker | The 3-Person Company That Shouldn’t Exist: Building an AI-Enhanced Enterprise from the Ground Up | 1
| 11:15am - 12:00pm | 3 Block B | Lead Adoption | Esquimalt | Ready to announce | Davis Neable | TBD |  | Confirmed - Davis is away this week and will get back
| 1:30pm - 2:15pm | 4 Block C | Stage | Main Theatre | Confirmed, details in progress | Anu to organize panel | TBD |  | SM: Reached out to Anu on Aug 25 for title/details
| 1:30pm - 2:15pm | 4 Block C | Builder Deeper | Oak Bay | Ready to announce | Miles Garvey & Gabriel Gaultier | Lightning Talk: Enterprise data for AI | I put 3 | John reached out to Miles & Gabriel and they seemed open to a combined lightning talk
| 1:30pm - 2:15pm | 4 Block C | Work Smarter | Saanich | Ready to announce | Jacques Du Plessis & Houtan Mashinchi | AI Contracts & Due Diligence: What Operators, Founders, and Investors Need to Know | They said 2 or 3, I put 1
| 1:30pm - 2:15pm | 4 Block C | Lead Adoption | Esquimalt | Ready to announce | Rachel Krayenhoff van de Leur | The Future of the Business Operating System | I put 1 - asked Rachel to confirm
| 2:30pm - 3:15pm | 5 Block D | Stage | Main Theatre | Ready to announce | Dr. Sue Abu-Hakima | How to Build AI Startups and Multi-Agent Platforms to Exit |  | SM: Reached out to Sue for details / headshot on Aug 25
| 2:30pm - 3:15pm | 5 Block D | Builder Deeper | Oak Bay | Ready to announce | Tom Myer | The Attacker's Lens: Threat Modeling for AI and Agentic Systems | 2
| 2:30pm - 3:15pm | 5 Block D | Work Smarter | Saanich | Ready to announce | Arsh Singh to moderate, Sheila Wynne Fung, Ian Slipp (confirmed), Alex McKeachie and Owen Mead-Robins invited. | Why AI Fails at Small Businesses (And How the Winners Get It Right)
| 2:30pm - 3:15pm | 5 Block D | Lead Adoption | Esquimalt | Ready to announce | Andrea Shillington & Bibi Brahim | The Sovereignty Curve: The AI Strategy You'll Wish You'd Started Today | 2
| 3:20pm - 4:00pm | 6 Closing | Stage | Main Theatre | Ready to announce | Panel Moderator: Robert Cooper Peter Scott, Christine Tatham, Jenifer Hufnagel and Eric McLachlan have confirmed - one more possible addition but can add it later. | Growing Your Career & Business with AI: Surviving and Thriving in an AI Era

## Speaker Contacts
First Name | Last Name | Email | Organization | Invitation Email | Notes | Speaker card?
Diane | Giutw
Sid | Shrinivasan | sshrinivasan@gmail.com | Crux Intelligence | Sent |  | Y
Emma | Irwin | emma.irwin@gmail.com | Open Practice | Sent |  | Y
Anthony | Bortolussi | anthonybortolussi@outlook.com | Create Video Agency | Sent |  | Y
Chace | Cade | Cade@saasberry.ai | saasberry | Sent
Davis | Neable | davisneable@gmail.com | lululemon | Sent |  | Y
Kris | Krüg | kk@bc-ai.ca | BC + AI Ecosystem Association | Sent |  | Y
Rob | Parker | rob.parker@primehealthapp.com | Prime Health | Sent |  | Y
Jacques | Du Plessis | jduplessis@osler.com | Osler | Sent | Multi-speaker session, also Houtan Mashinchi | Y
Rachel | Krayenhoff van de Leur | rachel@ingenuitylabs.ca | Ingenuity Labs | Sent |  | Y
Dr. Sue | Abu-Hakima | s7878@alstari.com | Alstari | Sent |  | Y
Tom | Myer | myerman@gmail.com | ? | Sent |  | Y
Andrea | Shillington | andrea@comfrey.ai | Comfrey AI | Sent |  | Y
Bibi | Brahim | brahim@comfrey.ai | Comfrey AI | Sent |  | Y
Anu | Jolliffe | anu@greyskytech.com | Grey Sky Tech | Sent
Rene | Fournier |  |  |  | Panel member, Sam hasn't contacted yet
Miles | Garvey | miles@brabble.io | Brabble | Sent | John to contact with Gabriel | Y
Gabriel | Gaultier | gabriel@missinglinkanalytics.com | Missing Link Analytics | Sent | John to contact with Miles | Y
Robert | Cooper | rob@plusroi.com | Plus ROI Marketing
John | Oram | john@veilstream.com | VeilStream
Mike | Anderson | mike@andersonapps.ca
Calum | Bird | calum@trelent.com | Trelent
Jeremy | Moseley | jeremy.moseley@gmail.com | Microsoft
Greg | Jonson

## Removed from Speaker Contacts
First Name | Last Name | Email | Organization | Invitation Email | Notes
Rishi | Behari | behari.rishi@gmail.com |  | Sent

## Dropdown Lists
Status | Description
Not planned | Speaker(s) have not yet been engaged.
Still tentative | Speaker(s) have been approached, but not yet confirmed
Confirmed, details in progress | Speaker(s) have confirmed their participation, but details such as bios, session description, etc. are still being collected
Ready to announce | Information is ready to be shared on social media and in the conference program
Session Blocks
1 Welcome & Morning Keynote
2 Block A
3 Block B
4 Block C
5 Block D
6 Closing
Rooms
Main Theatre
Oak Bay
Saanich
Esquimalt
Technical Rating | Description
1 Introductory | Open to everyone, no technical background needed. Sessions at this level focus on big-picture ideas, practical use cases, and strategy. Expect minimal jargon and accessible explanations.
2 Intermediate | Still welcoming to all, but you may hear some technical terms or tool names. These sessions assume a basic familiarity with data and AI concepts and go a bit deeper into how things work.
3 Advanced | Everyone is welcome, but expect a faster pace and more technical detail. These sessions are geared toward practitioners and may include code, models, or architecture diagrams. If you're new, don’t worry — just know it might get jargon-heavy!
Tracks
Stage
Builder Deeper
Work Smarter
Lead Adoption